{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["List1","List2","List3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"List1","index":0,"n_rows":50,"n_cols":7,"rows_kept":50,"cut":false,"hidden":false,"merged":[[47,0,47,4],[0,1,0,4]],"flags":["formulas_cached_only"]}
[null,"POPIS DEL ZA REKONSTRUKCIJO OBSTOJEČEGA VODOVODA V BUDANJAH - Severska vas"]
[]
[]
["Zap. št.","Opis del","Količina","Enota","Cena na enoto","Vrednost "]
[null,"Budanje od št 89 do št. 94"]
[]
["I.","PRIPRAVLJALNA DELA"]
[1,"Priprava in organizacija gradbišča pred pričetkom del na trasi (dovoz mehanizacije, ureditev deponij za cevi ter odvečni material,..).",1,"kompl.",0,0]
[2,"Zapora ceste z ustrezno dokumentacijo ter signalizacijo v času gradnje",1,"kompl.",0,0]
[3,"Zakoličenje trase obstoječega vodovoda.",105,"m",0,0]
[4,"Zakoličba križanj tras vodovoda z ostalimi komunalnimi vodi.",4,"kos",0,0]
[5,"Izdelava začasne vodovodne prevezave (by-pas) za čas gradnje, s PE 80 cevjo premera 32 mm, 12.5 bar.Potrebna je povezava 5 priključkov, z začasno demontažo vodomerov.",1,"kompl.",0,0]
[6,"Obveščanje potrošnikov o motnjah v oskrbi z vodo",1,"kompl.",0,0]
[null,"PRIPRAVLJALNA DELA SKUPAJ",null,null,null,0,"Eur"]
[]
[]
["II.","ZEMELJSKA DELA"]
[1,"Rušenje asfaltnega cestišča debeline 8 cm, s pravilnim odrezom robov, nakladanjem in odvozom na deponijo na razdalji do 5 km.",84,"m2",0,0]
[2,"Rušenje robnikov z vzpostavitvijo v prvotno stanje.",4,"m",0,0]
[3,"Strojni izkopi jarka za vodovod širine 0,6 m do 1 m in globine 1,0 do 1,3 m v zemljini III. - IV. kat.",76,"m3",0,0]
[4,"Ročni izkopi okrog obstoječih cevi širine 0,6 m do 1,0 m in globine 1,0 do 1,3 m v zemljini IV. kat.",2,"m3",0,0]
[5,"Planum naravnih temeljnih tal v zemljini III. kat. s točnostjo +- 3 cm po predvidenem naklonu.",63,"m2",0,0]
[6,"Izdelava peščenega nasipa nad cevjo debeline 10 cm iz peska granulacije 0-4 mm. ",6,"m3",0,0]
[7,"Strojno zasipavanje jarka pod asfaltnim cestiščem s tamponom 0-30mm. Zasip je treba nabijati v plasteh po 30 cm. ",63,"m3",0,0]
[8,"Nakladanje, odvoz in razkladanje odvečnega materiala na deponijo do 5 km.",76,"m3",0,0]
[9,"Razrez in dstranjevanje obstoječih AC cevi DN 80 mm ter odvoz na deponijo komunalnih odpadkov.",105,"m",0,0]
[10,"Priprava in krpanje z asfaltom granulacije do 11 v debelini 8 cm",84,"m2",0,0]
[11,"Izdelava geodetskega posnetka in vnos v kataster komunalnih vodov.",105,"m",0,0]
[null,"ZEMELJSKA DELA SKUPAJ",null,null,null,0,"Eur"]
[]
[]
[]
["III.","MONTAŽNA DELA IN VODOVODNI MATERIAL"]
[]
[null,"OPOMBA: Vsa vodovodna armatura, fazonski kosi in cevi morajo biti izdelani za pritiske do 16 bar. "]
[1,"Dobava, montaža pocinkanih cevi s trdo PVC izolacijo DN 40",105,"m",0,0]
[2,"Dobava, montaža in tesnenje FF kosa, l=800 mm, DN 100 mm.",1,"kos",0,0]
[3,"Dobava, montaža in tesnenje T kosa, DN 100/50 mm.",1,"kos",0,0]
[4,"Dobava, montaža in tesnenje EURO zasuna, z vgradno armaturo in cestno kapo, DN 50 mm, tip 23 PN 16.",1,"kos",0,0]
[5,"Dobava, montaža in tesnenje odcepnega EV zasuna 1\" ",4,"kos",0,0]
[6,"Dobava, montaža pocinkanih cevi 1\" s trdo PVC izolacijoter ter ustrezno izolacijo spojev z dekorodalom in plastizoloin.",30,"m",0,0]
[7,"Dobava, montaža univerzalne enojne spojke za cev DN 100 s tesnenjem",2,"kos",0,0]
[8,"Izdelava in namestitev prefabriciranih  podložnih plošč za hidrante, zasune, odcepe in cestne kape.",5,"kos",0,0]
[9,"Tlačni preizkus",105,"m",0,0]
[10,"Izpiranje sistema ter dezinfekcija",105,"m",0,0]
[null,"MONTAŽNA DELA IN VODOVODNI MATERIAL SKUPAJ",null,null,null,0,"Eur"]
[]
["Gradbena in Strojnoinstalacijska dela skupaj  v Eur",{"$nulls":4},0,"Eur"]
[]
[null,"Opomba: V Budanjah je v planu za leto 2010 tudi sanacija dela vodovoda v \"Logu\", v sklopu gradnje kanalizacije, v kolikor se bo gradila."]

{"sheet":"List2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"List3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}