{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Sheet1","Sheet2","Sheet3"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Sheet1","index":0,"n_rows":64,"n_cols":6,"rows_kept":64,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[null,"POPIS DEL - SERVISNA CESTA ČRNIČE"]
[]
[]
[null,"CESTA",null,null,null,0]
[null,"JR - GRADBENA DELA"]
[null,"SKUPAJ",null,null,null,0]
[null,"Popust",null,null,null,0]
[null,"DDV - 20%",null,null,null,0]
[null,"VSE SKUPAJ",null,null,null,0]
[]
[]
[]
["šifra",null,"SKUPAJ","ENOTA","cena za enoto","znesek"]
[]
[]
["1.","PREDDELA"]
["1.1.","Obnovitev in zavarovnje zakoličbe trase",0.25,"Km",0,0]
["1.2.","Postavitev in zavarovanje prečnih profilov",10,"KOS",0,0]
["1.3.","Posek in odstranitev grmovja in dreves",30,"m2",0,0]
["1.4.","Demontaža prometnih znakov",1,"KOS",0,0]
[null,"Izvedba potrebne signalizacije za označitev gradbišča na regionalni cesti R2-444 Ajdovščina-Nova Gorica",null,null,null,0]
[]
["2.","ZEMELJSKA DELA IN TEMELJENJE"]
["2.1.","Široki izkopi lahke zemljine z nakladanjem na prevozno sredstvo ter odvoz na deponijo do 10 km",470,"m3",0,0]
["2.2.","Vgrajevanje nasipov iz naravno pridobljene lahke zemljine",0,"m3"]
["2.3.","Izdelava posteljice v debelini plasti 40 cm",220,"m3",0,0]
["2.4.","Humuziranje brežin brez valjanja",500,"m2",0,0]
["2.5.","Dobava in vgraditev škarpnikov 45x50x18 (ŠxDxV)",23,"m2",0,0]
["2.6.","Rušenje obstoječega asfalta, debeline do 8 cm, z nakladanjemna vozilo in odvozom v mestnodeponijo na razdalji do 5 km",300,"m2",0,0]
["2.7.","Rezanje asfalta debeline do 12 cm",40,"m",0,0]
[]
[]
[]
["3.","VOZIŠČNA KONSTRUKCIJA"]
["3.1.","Izdelava nevezane plasti gramoza v debelini od 21 do 30 cm",90,"m3",0,0]
["3.2.","Izdelava s cementom vezane (stabilizirane) nosilne plasti gramoza v debelini 15 cm",0,"m2"]
["3.3.","Ročna izvedba obrabno zaporne plasti BB 11 6cm",50,"m2",0,0]
["3.4.","Izdelava zgornje nosilne plasti iz asfaltne zmesi bituminiziranega drobljenca 0/22S,5cm",400,"m2",0,0]
["3.5.","Izdelava zgornje nosilne plasti iz asfaltne zmesi bituminiziranega drobljenca 0/16",0,"m2"]
["3.6.","Izdelava obrabnozaporne plasti bitumenskega betona  BB11s v debelini 4 cm",400,"m2",0,0]
["3.7.","Vgraditev predfabriciranih dvignjenih robnikov iz cementnega betona 15/25 cm",100,"m1",0,0]
["3.8.","Vgraditev obrob iz malih tlakovcev (kock) iz naravnega kamna 10/10/10 cm",50,"m1",0,0]
["3.9.","Izdelava humuzirane bankine, širine do 0.5 m",220,"m2",0,0]
[]
[]
["4.","ODVODNJAVANJE"]
["4.1.","Izdelava vzdolžne in prečne drenaže globine so 1 m, plastične cevi premera 10 cm",10,"m1",0,0]
["4.2.","Izdelava kanalizacije iz PVC cevi, premera 25 cm",40,"m1",0,0]
["4.3.","Izdelava betonskega jaška premera 40 cm, globine 1.5 do 2.0 m",2,"KOS",0,0]
["4.4.","Izdelava betonskega jaška premera 60 cm, globine 1.5 do 2.0 m",2,"KOS",0,0]
["4.5.","Ureditev ponikovalnice z betonskimi cevmi, premra 80 cm, globine 1.1 do 2.0 m, dolžine 22m, zasutje z drenažnim materialom, zaščita z filcem",1,"KOS",0,0]
[]
[]
["5.","PROMETNA OPREMA"]
["5.1.","Dobava in postavitev dvojnega prometnega znaka, kompletno s temeljem",2,"KOS",0,0]
["5.2.","Dobava in postavitev enojnega prometnega znaka , kompletno s temeljenjem",2,"KOS",0,0]
["5.3.","Dobava in pritrditev prometnega znaka, velikost 1500x400 mm",2,"KOS",0,0]
["5.4.","Dobava in pritrditev prometnega znaka, velikost 4500x2400 mm",0,"KOS",0,0]
["5.5.","Izdelava tankoslojne neprekinjene označbe z enokomponentno belo barvo, širine 12 cm",100,"m1",0,0]
["5.6.","Izdelava tankoslojne neprekinjene označbe z enokomponentno belo barvo, širine 10 cm",100,"m1",0,0]
["5.7.","Izdelava tankoslojne neprekinjene označbe z enokomponentno belo barvo, širine 50 cm",16,"m1",0,0]
[null,"SKUPAJ",null,null,null,0]

{"sheet":"Sheet2","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}